## Slide 1: AA117 T-Minus Plan April 2026 – October 2027 Driving Full Expenditure Through Structured Oversight & Strategic Reallocation
Parris Drakeford
Program Analyst

## Slide 2: The Big Picture
🎯 Strategic Objective
100% Expended | 0% Unobligated | 100% Reimbursements Submitted
How We Get There:
Early Activation
Continuous Monitoring
Mid-Cycle Correction
Formal Reallocation Decision
Structured Closeout

## Slide 3: Phase 1: Launch & Monitor (Apr–Sep 2026)
🚀 Launch
Projects initiated
Contracts executed
Funds encumbered & obligated ≥10% Expended
🔎 Monitor
Financial status review
Identify funds at risk
LHD Spending Plan submission ≥35% Expended

## Slide 4: Phase 2: Correct & Reallocate (Oct 2026–Mar 2027)
⚡ Accelerate
🔁 Reallocation Decision Point
Comprehensive fiscal review
Formal reallocation proposals submitted
DPH redistribution determinations
≥70% Expended
Implement contingency actions
Revise scopes/timelines
Increase spending velocity
≥55% Expended

## Slide 5: Phase 3: Deploy & Execute (Apr–Sep 2027)
📈 Full Deployment
Accept redistributed funds
Finalize procurements
Intensify implementation 100% Encumbered/Obligated ≥85% Expended
✅ Final Implementation
Complete activities
Resolve compliance issues ≥95% Expended 0% Unobligated

## Slide 6: Closeout (Oct 2027)
🏁 Final Spending & Reporting
Complete all expenditures
Submit final reimbursements
Submit final fiscal & programmatic reports
Final Outcome
100% Expended 100% Reimbursements Submitted Zero Lapsed Funds