## Action Items - In progress
Category | Recommendation | Impact | Effort | Proposed Lead | Supporting Partners | Target Timeline (Tentative) | Barriers / Notes | Status
Comms | Establish a multi-layered communications contingency plan (PACE plan) that integrates diverse back-up solutions, enhances interoperability, and expands access to emergency communication tools. | 3 - High | 1 - Low | Kelley | IT, DPH, ESF-2 | 2026 - Q1 | Have a draft, needs to be refined with partners, will intersect with other plans - looking towards January | 11/18: In progress. Updating Risk Communications Plan, which will include PACE plan. Will review with partners during Q3.
Plans | Formalize the Disaster Support Unit to serve as dedicated liaisons to assist with bridging the communications gap between state operations and local needs. | 3 - High | 1 - Low | Lori | Stacie/Patrick/Angel | 2026 - Q2 | Created during Helene, just needs to be added to existing plans; Update in progress; Will coincide with All Hazards updates | 11/18: In progress. Will be included as part of AHP updates.
T/E | In future planning exercises, prepare for instances in which communications infrastructure has completely broken down and how formal information channels would need to be adapted or less heavily relied upon. | 3 - High | 1 - Low | Kelley | Exercise Planners | 2028 | Inject into natural disaster exercise; smaller components built into earlier exercises (2026 and beyond) | 11/18: No updates yet.
Demob | Develop a standard exit report that sections complete to summarize response and indicate standdown. | 2 - Medium | 1 - Low | Sandi | Kelley/Laura | Start of hurricane season 2026 | ReadyOp survey to be created | 11/18: No updates yet.
Response Culture | Develop clearly defined decision-making processes that empower public health representatives in the SEOC. | 2 - Medium | 1 - Low | Brian | Zack/Amanda | End of October 2025 | Decision maker has to be at the desk | 11/18: In progress. Drafting language to update SOP to include experienced and non-experienced staff.
Response Culture | Conduct targeted briefings on SEOC roles, response mindset, expectations, and coordination protocols to ensure public health representatives understand their emergency response obligations and decision-making responsibilities. | 2 - Medium | 1 - Low | Val | Laura | End of October 2025 | 815 shift brief will start to include this info | 11/14: Began implementing this in Erin and Imelda during the 8:15 briefing. Have taken note from feedback to begin briefing earlier.
T/E | Develop and conduct planning exercises that include regional attendees (e.g., from the eastern and western parts of the state) to prepare for cross-regional response, address potential resource gaps, and develop cross-regional protocols. | 3 - High | 3 - High | Laura |  | Natural disaster exercise - 2027 | Incorporate into natural disaster exercise - 2027; A lot of planning and coordination, but already in the works as well. Need to ensure more DPH partners are at the table. | 11/13: No Update
Deployment | Develop protocols to identify, recruit, and integrate personnel from unaffected parts of the state to support affected regions. | 3 - High | 2 - Medium | Laura/Val | Tim/LHDs | 2026-06-01 | In progress; requires a lot of training once protocols are developed | 11/13: In progress; Job Action Sheets for Public Health Assistance Teams being reviewed and edited. Still need trainings.
Plans | Evaluate existing preparedness and response plans to verify that plans are scalable and planning assumptions are grounded in reality, account for changing disaster behavior, adequately identify regional gaps. | 2 - Medium | 2 - Medium | Lori |  | 2026 - Q2 | Mainly applies to AHP | 11/13: In progress; workshops to be scheduled with DPH partners to integrate input
Plans | Develop a division wide response plan that integrates all branches/sections, defines emergency roles and responsibilities, outlines expectations and decision makers, and emphasizes a richly “socialized system” as a clear goal. | 3 - High | 3 - High | Lori |  | 2026 - Q2 | Being addressed in all hazards plan updates | 11/13: In progress; workshops to be scheduled with DPH partners to integrate input
Plans | Develop a Continuity of Operations plan for each branch within NCDPH to assist staff in prioritizing which of their daily tasks can be paused while in an active response. | 3 - High | 3 - High | Travis |  | Phase 1: June 2026 | In progress | 11/13: In progress; workshops to be scheduled with DPH partners to integrate input
Plans | Socialize and update plans with all NCDPH sections on an annual or bi-annual basis. | 2 - Medium | 2 - Medium | Laura | Brian |  | Plan updates in progress, but socializing piece is difficult (Town Hall? DMT?) | 11/13: In Progress
T/E | Develop training and exercise plans for all staff within NCDPH that have or may have a role in future response activities. | 3 - High | 3 - High | Brian | Laura |  |  | 11/13: In progress; independent study policy already sent to Epi leadership; re-energizing effort to codify advanced course requirements with SMT in 2026

## Action Items - Future
Category | Recommendation | Impact | Effort | Proposed Lead | Supporting Partners | Target Timeline (Tentative) | Barriers / Notes | Status
Activation | Develop and socialize a time-delineated schedule that outlines response activities by anticipated timelines, including the ability to scale for no-notice events. | 3 - High | 2 - Medium | BMT |  |  | Can work on during retreat, then will update SOG
Finance/Admin | Develop flexible internal mechanisms to purchase supplies (e.g., a standardized catalog of purchasable supplies) during periods where formal systems are unavailable. | 3 - High | 2 - Medium | Val |  |  | Some aspects may be lower effort, but overall, changes to policy will require more effort.
Finance/Admin | Establish temporary vendor-approval protocols during pre-disaster planning for urgent resource requests during emergencies (akin to pre-approvals during COVID). | 3 - High | 2 - Medium | Tim | CDB |  | Distributors license is move dependent
Finance/Admin | Create modular resource assessment and procurement components that allow adjustments based on the specific crisis type (e.g., public health emergencies vs. natural disasters). | 3 - High | 2 - Medium | Wayne | BMT support |  | May be involved with the above recommendations
Plans | Evaluate operational organizational chart to determine and socialize gray-sky chains of command and reporting structures. | 3 - High | 2 - Medium | Brian | Zack/Amanda/Laura |  | No division-wide org chart currently; ties into broader division AH planning need identified elsewhere
T/E | Conduct scenario-based exercises that mimic real emergency conditions and worst-case scenarios, where plans fail and must be quickly adjusted to reinforce rapid decision-making, contingency planning, flexibility, and adaptability. | 3 - High | 2 - Medium | Laura |  |  | Incorporate into natural disaster exercise - 2027; Make sure using AAR and IPs to refine plans.
T/E | Establish a structured process for identifying bottlenecks and making rapid adjustments to support efficient response and minimize informal networks | 2 - Medium | 2 - Medium | Laura |  |  | Incorporate into natural Disaster exercise - 2027; Best implemented during exercises; can add agenda item during coordination meeting to address bottlenecks (or something similar)
T/E | Schedule routine operational reviews at key intervals to identify emerging bottlenecks | 2 - Medium | 2 - Medium | Laura |  |  | Incorporate into natural Disaster exercise - 2027; Best implemented during exercises; can add agenda item during coordination meeting to address bottlenecks (or something similar)
T/E | Assign dedicated individual or team representatives within the SEOC and/or IMT to monitor response effectiveness, document process inefficiencies, and facilitate immediate problem-solving. | 2 - Medium | 2 - Medium | Laura |  |  | Incorporate into natural Disaster exercise - 2027; Best implemented during exercises; can add agenda item during coordination meeting to address bottlenecks (or something similar)
Demob | Develop a demobilization annex in existing plans that establishes objectives, considerations, final resource planning, and a communication plan that articulates the demobilization process in advance. | 1 - Low | 2 - Medium | BMT |  |  | All sections need a demob plan.Plan leads are responsible for their section plans.
Demob | Develop and incorporate system for redistributing or storing non-perishable surplus supplies as part of resource management demobilization process. | 3 - High | 3 - High | Pause |  |  | This would be best to figure out once move has been completed and other resource issues have been addressed.
Plans | Ensure that department and division directors, as well as response leadership, understand the importance of each branch’s role in the response and identify a structure for supporting their roles. | 3 - High | 3 - High | Brian |  |  | Requires integration of DPH into plans, roles and responsibilities; Structure for support will be most challenging part
Activation | Implement a NCDPH incident action planning process that develops a uniform set of information and goals pertinent to every section to ensure that they operate in concert. | 2 - Medium | 3 - High | Brian | Laura
Activation | Develop/refine process for collecting and assessing data in impacted areas to inform supply purchases (e.g., water sample kits, disinfection kits). | 2 - Medium | 3 - High | Tim/Val
Deployment | Establish regional staging areas for deployed EHS and PHN staff to provide centralized coordination where responders can receive briefings, adjust plans based on updated field conditions, and optimize distribution routes before moving into impacted areas. | 1 - Low | 3 - High |  |  |  | Being handled virtually, can be utilized if needed, but otherwise, virtual briefing/staging is preferred and working
Activation | Engage and empower specialized personnel from within and outside of the state, embedding them to guide department and division heads. | 1 - Low | 1 - Low |  |  |  | Unclear